# Team Charter: Outdoor Travel Project

## Project Overview

The project involves designing and developing a hiking and outdoor adventure website that provides detailed travel information, community oriented features, and multi-media compatibility for uploads. The website will include weather and ferry data, localized tips and information, user accounts, blogs/comments, and administrative tools for content management. The target audience includes the client’s friends, family, and outdoor enthusiasts, with an eventual goal of reaching broader audiences visiting the Pacific Northwest.

Deadline: December 15
Team Size: 4 Members
Client: Independent Project (funded by client)
Budget: $3,000 initial, up to $200 monthly maintenance

## User Stories

- As an outdoor enthusiast planning a trip, I want to view detailed information about hiking and travel destinations - including how to get there, difficulty levels, real-time weather, and ferry schedules, so that I can plan my experience easily from one place.

- As an international visitor, I want to be able to translate the site into my preferred language so that I can understand travel information clearly and feel included as part of the community.

- As a friend or member of the site, I want to securely log in to access exclusive content so that I can receive insider tips and special information.

- As a user who has visited a location, I want to leave comments and share my own experiences so that I can engage with others and contribute to a growing outdoor community.

- As an administrator, I want to easily upload photos and add new adventures without needing technical support so that the site stays current and reflects my journeys.

- As an outdoor guide, I want the ability to list my offerings so that I can connect with interested users and potentially generate income through the platform.

## Project Goals

- Launch a functional website that provides:

  - Destination information, weather, and ferry details.

  - User login and membership system with role-based access.

  - Blog/comment section for shared user experiences.

  - Administrative panel for easy photo and adventure uploads.

- Ensure scalability for:

  - Future monetization features (membership tiers, guide listings).

  - Multilingual translation support.

  - Integration with external data sources (weather, ferry, maps).

- Deliver a clean, user-friendly design optimized for both desktop and mobile.

- Deploy to a reliable cloud host (AWS [EC2/S3], Azure, or equivalent).

## Team Roles and Responsibilities

### Developer: Josh’ua Monsalvatge

Responsibilities:

- Coordinate scope, milestones, and weekly Monday agendas.

- Maintain client communications and change control.

- Own roadmap, risk tracking, and release management.

### Developer: Carlos Valencia

Responsibilities:

- Backend services, authentication, role-based access.

- External integrations (weather API, ferry data, maps).

- Infrastructure-as-code and cloud deployment pipeline.

### Developer: John Nelson

Responsibilities:

- Test strategy, automation, and regression suites.

- Documentation, runbooks, and admin content workflows.

- UAT coordination and defect triage/resolution tracking.

## Communication Protocols

- Primary Communication: Email (for client updates).

- Team Collaboration: Discord or Slack (for internal communication).

- Progress Tracking: Trello, Miro, or Notion boards (task assignments, milestones).

- Meeting Cadence:

  - Weekly team meeting every Monday (status review, sprint planning, blockers).

  - Weekly client update via summary email following Monday meeting.

  - Urgent communication through agreed chat platform.

## Project Timeline (Aligned with Monday Meetings)

| Week | Date | Focus | Deliverables / Milestones |
| --- | --- | --- | --- |
| Week 1 | Oct 28 | Project Kickoff | Review client transcript, confirm goals, assign team roles, create task board. |
| Week 2 | Nov 4 | Discovery & Planning | Complete user stories, draft requirements doc, initial wireframes, finalize tech stack. |
| Week 3 | Nov 11 | Design & Architecture | Approve final wireframes, create UI mockups, outline database schema and architecture plan. |
| Week 4 | Nov 18 | Development Phase 1 | Build homepage, hiking info section, and integrate weather and ferry APIs. |
| Week 5 | Nov 25 | Development Phase 2 | Implement login/membership system, blog/comments, and admin features. |
| Week 6 | Dec 2 | Testing & Refinement | Conduct functionality tests, fix bugs, finalize design polish and responsiveness. |
| Week 7 | Dec 9 | Launch Preparation | Perform client review, finalize deployment setup, deliver documentation. |
| Week 8 | Dec 15 (Sunday Deadline) | Final Delivery | Website fully live by end of day Dec 15; post-launch verification and client approval. |

## Quality and Testing Criteria

- User login and access control verified through role-based authentication.

- Real-time data from weather/ferry APIs displayed correctly.

- Site translation functions for multiple languages without data loss.

- All pages pass responsiveness and performance benchmarks.

- Content uploads validated for both client and admin roles.

## Risk Management

- Scope Creep: Controlled through client-approved change requests.

- Time Delays: Managed via Monday reviews and sprint accountability.

- Technical Issues: Mitigated through version control (GitHub branches) and weekly testing.

- Budget Constraints: Prioritize essential features; postpone non-critical enhancements.

## Core Values

- Respect and Inclusion — Every team member’s input is valued; we listen before responding and ensure equal participation.

- Accountability — We take ownership of our assigned tasks and communicate proactively when challenges arise.

- Transparency — We maintain open, honest communication and share progress, setbacks, and updates regularly.

- Collaboration — We build solutions together, recognizing that teamwork produces higher quality results than isolated effort.

- Continuous Improvement — We seek feedback, reflect on our work, and refine both our process and product continuously.

## Success Criteria

- Website live and functional by December 15.

- Client able to upload, manage, and update site content independently.

- Users can access accurate, engaging, and localized travel data.

- Future roadmap documented for mobile app and monetization features.